## Sheet1
Priority	Story	#REF!	Category	Sprint	Status	Completed on	Type
1	As a sleepy person I want to be able to create alarms in order to wake up.	10	General	1			Story
2	As a person with bad memory I want to see when the alarm will ring.	5	General	1			Story
3	As a person that sometimes need to offset alarms from day to day I want to quickly change the time.	5	General	1			Story
4	As a person with varying needs and circumstances, I want to have the option to remove alarms I no longer need to reduce the items I need to manage in my life.	5	General	1			Story
5	As a person who just needs to wake up, I want to hear a simple ringtone in order to wake up.	15	Sound				Story
6	As a person with many different needs in varying times, I want multiple alarms in order to track different events.	10	General				Story
7	As an orderly person I want to be able to name my different alarms, in order to remember for what I've used it.	7	General	1			Story
8	As a person who plans ahead, I want to be able to setup the alarm to always go off at a particular time on a particular weekday.	15	General				Story
9	As a person with bad short term memory I want to see in how much time the alarm will ring.	5	General	1			Story
10	As a human being in general I want to set repeating alarms so I don’t have to do unnecessary work.	10	General				Story
11	As a person that sleeps deep, I want to complete challenges in order wake up.	15	Challenge				Epic
12	As a user who likes doing math I want to complete a math challenge to stop an alarm, in order to ensure me waking up and at the same time enjoy it.	10	Challenge				Story
13	As a person who sometimes sorts similar numbers incorrectly, I would like a challenge involving sorting them descendingly or ascendingly in order to wake up me up.	10	Challenge				Story
14	As someone who forgot to turn off their alarm, and it goes off in an inconvenient situation, I want to turn it off quickly, in order to not embarrass myself.	10	General				Story
15	As a user who wants to do things quickly I want to copy an alarm entry, in order to get a very similar one with just some feature changed.	10	General				Story
16	As a snake lover I want to play a Snake game to shut the alarm off, in order to get myself to focus and not fall back to sleep.	25	Challenge				Story
17	As a person with terrible short-term memory I want to be challenged by a memory problem every morning.	20	Challenge				Story
18	As a person that sometimes want to sleep a bit more I want to snooze the alarm for a given time.	10	General				Story
19	As a user I want to make the phone vibrate to when the alarm goes off, in order to wake me up faster.	10	Vibration				Story
20	As a user I want the vibration to stop once I've started working on a challenge.	10	Vibration				Story
21	As a lazy person, I want to set a global preset for options not set in individual alarms, in order to not configure everything.	15	General				Story
22	As a user I want to set the volume for a specific alarm, in order to have many alarm that are of variable volume.	10	Sound				Story
23	As a user I want to have the alarm increase in volume over time, so I can wake up at as low volume as required, in order to not disturb other people in my environment, but also ensure that I cannot ignore the alarm for too long.	15	Sound				Story
24	As a person who wants to be further challenged I want a competing element that gives me points when a challenge is completed and removes points when I snooze in order to avoid snoozing.	10	Challenge				Epic
25	When I emergency-cancel a challenge alarm I want to lose points in order to not abuse the system.	5	Challenge				Story
26	As a person who often gets up on the wrong side of the bed, I want to be able to chose whether the alarm should be more silent during a challenge.	7	Sound				Story
27	As a music lover I want to hear music when I wake up in order to feel good.	30	Sound				Epic
28	As a person who risks failing to wake up due to snoozing, I want my alarm to ring louder and louder for every time I press “snooze”.	7	Sound				Story
29	As a person who likes to solve puzzles, I want to be challenged with a (3x3) puzzle where I order pieces visually to make an image.	20	Challenge				Story
30	As an experienced mathematician I want to set the degree of difficulty.	30	Challenge				Story
31	As a spotify user, I want to be able to select music from Spotify, in order to have a pleasant wake-up experience.	250	Spotify/Sound				Epic
32	As a person that sometimes find phone triggering the alarm in a lecture or embarrassing situation I want to select geographic areas with GPS that do not trigger alarms. I want to select them via making polygons by tapping points in Google Maps on the phone	250	GPS				Epic
33	As a person that want to interact with my alarm in the phone as a more physical device I want to use flipping, shaking, and the native volume, power buttons for different actions.	30	General				Epic
34	As a person with multiple devices I want the ability to sync my alarms via devices.	30	Sharing				Epic
35	As a person that prefers other languages than the standard set by the developers I want internationalization in order to use the alarm easier.	10	Internationalization				Epic
36	As a person that needs to do things fast in the morning, I want to be informed of my immediate environment via speech.	30	Speech				Epic
37	As a person in a stressful environment I need to know the time immediately via speech, when I wake up in order to know how much I should hurry.	10	Speech				Story
38	As a person that doesn’t have time to look out the window I want to be informed of the weather in order to pick appropriate clothing.	15	Speech				Story
39	As a frequent user of URI, I want to employ URI to share alarms.	25	Sharing				Story
40	As member of a group, I want the option to let my alarms send text messages to my comrades to simplify our cooperation and to minimise the collective work load.	15	Sharing				Epic
1/0	As an incurable troll I want the add-alarm icon to become a Christmas tree when Christmas is due, in order to get laughs		LOL				Story
1/0	As an programmer and incurable troll, I want to put easter eggs in order to for the lulz.		LOL				Story
	As a person that needs to sleep 8 hours whatever the time, I want to set the alarm to countdown and ring when the countdown is finished, in order to not have to calculate when 8 hours would be.	10	General				Story