## Sheet1
User story	Task(s)	Time estimate	Assigned to	Status	Completed on	Completed by	Priority	Day 1	2	3	4	5	6	7
As an orderly person I want to be able to name my different alarms, in order to remember for what I've used it.
	Implement in model		Mazdak	DONE	2013-09-18	Mazdak		0,1
	Have the name shown in the list		Niklas	DONE	2013-09-19	Niklas
	Change the name from the detailed alarm view
	Write test to check name validity (illegal chars etc.)?
	Add mechanism for alarm #1,2,3....

As a sleepy person I want to be able to create alarms in order to wake up.
	Add a menu button		Niklas	DONE	2013-09-18	Niklas
	Fix navigation so that one can go back to the previous activity			DONE
	Add functionality to choose time in the settings activity		Mazdak
	Add functionality to choose a name in the settings activity
	Make android alert user on time			PARTIALLY DONE
	Persist data to drive/something (SQLite via ORMLite?)			URGENT

As a person with bad memory I want to see when the alarm will ring.
	Implement in model		Johan	Done	2013-09-16	Johan
	Show in GUI		Niklas	Done	2013-09-18	Niklas
	Documentation		Niklas	Done	2013-09-18	Niklas, Mazdak
	Refresh in GUI when change occurs @ MainActivity		Mazdak	Done	2013-09-21	Mazdak
	Testing		Niklas, Eric	Done	2013-09-19
	Refresh in GUI when change occurs @ Detailed view.

As a person that sometimes need to offset alarms from day to day I want to quickly change the time.
	Add a button for detailed settings?
	Add a timedatepicker in MainActivity		Mazdak	Done	2013-09-21	Mazdak, Niklas

As a person with varying needs and circumstances, I want to have the option to remove alarms I no longer need to reduce the items I need to manage in my life.
	Add option in GUI to remove alarm		Niklas	DONE	2013-09-20	Niklas
	Bind GUI action with actual removal in model/database

As a person with bad short term memory I want to see in how much time the alarm will ring.		6	Mazdak, Eric
	Implement in model		Mazdak	DONE	2013-09-18	Mazdak, Eric		2
	Testing		Mazdak, Eric	DONE	2013-09-18	Mazdak, Eric
	Display the information in GUI		Mazdak	DONE	2013-09-18	Mazdak		3
	Refresh the GUI when a change occurs		Mazdak	DONE	2013-09-19	Mazdak
	Add switch global options: when / in how much time (diff)			WAITING